|  |
| --- |
| PS2Win |
| Project Planning Process |
| Keep Your Time |

|  |
| --- |
| Filipe Brandão  09-03-2013 |

Content

[1. Purpose 1](#_Toc350593119)

[2. Inputs and Outputs 1](#_Toc350593120)

[2.1. Inputs 1](#_Toc350593121)

[2.2. Outputs 1](#_Toc350593122)

[3. Activities 1](#_Toc350593123)

[4. Tools 2](#_Toc350593124)

[5. Related Processes 2](#_Toc350593125)

[6. Measures 2](#_Toc350593126)

**Images**

**Não foi encontrada nenhuma entrada do índice de ilustrações.**

**Tables**

[Table 1: List of Contribuitors ii](#_Toc350592681)

[Table 2: Version history ii](#_Toc350592682)

|  |  |  |  |
| --- | --- | --- | --- |
| **Authors and Contributors** | | | |
| **Date** | **Name** | **Contacts** | **Contribution** |
| 09-03-2013 | Filipe Brandão | a21180276@alunos.isec.pt | Author |
| 09-03-2013 | João Martins | a21170228@alunos.isec.pt | Author |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

Table 1: List of Contribuitors

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Revision History** | | | | | |
| **Date** | **Description** | **Author** | **Version** | **Approvers** | **State** |
| 09-03-2013 | Creation of first draft | Filipe Brandão & João Martins | 0.1 |  | Ready for Review |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |

Table 2: Version history

# Purpose

The main objective of this process is to produce adequate guidance to project team providing a central project plan.

# Inputs and Outputs

# Inputs

The input is the necessity of having a project plan.

# Outputs

A Software Development Plan that has centralized information about the project.

# Activities

Define a project plan:

* Define a project scope statement;
* Define the project life cycle;
* Define milestones;
* Identify the main deliverables;
* Create a top level work breakdown structure;
* Identify available resources;
* Estimation of effort for each task in the WBS. Poker planning must be used:
  + A moderator is identified;
  + Each team member has these cards: 1, 2, 3, 5, 8, 13;
  + The moderator reads the description of the task;
  + Every estimator selects an estimate card and places it face down on the table. After all estimates are in, the cards are flipped over;
  + If the estimates vary widely, the owners of the high and low estimates discuss the reasons for diverging. All estimators should participate in the discussion, 3 minutes max;
* Resource allocation to tasks;
* Create a Gantt diagram for the project schedule;
* Define quality objectives;
* Identify supporting plans;

# Tools

SmartDraw will be used to create Gantt Diagram.

Poker Planning estimation with a deck of cards.

# Related Processes

Risk Management Process.

Review Process.

Project Assessment and Control Process.

# Measures

The measures to take into account as far as documents are:

* The number of failed Milestones.
* The number of delayed tasks.

These measures are identified in “Project Planning Measures”.