## Slide 1: MIS – PS Keep Your Time

## Slide 2: Content

## Slide 3: Product Overview
João Martins

## Slide 4: Product Overview

## Slide 5: Product Overview

## Slide 6: Product Overview

## Slide 7: Project Managment
Filipe Brandão

## Slide 9: Product
João Martins

## Slide 11: Requirements
Number of Initial Requirements
66
Number of Delivered Requirements
64

## Slide 12: Requirements
Requirements | Nº | Requirements Delivered | Requirements not Delivered
Functional | 53 | 51 | 2
Interface | 11 | 11 | 0
Performance | 2 | 2 | 0
Total | 66 | 64 | 2

## Slide 13: Requirements conclusion
97% of the Requirements were delivered
Requirements not Delivered:
12CIT-003:ConfigureInactiveTime.Validate.False
1CT-004:Task.create.AutoComplete
Notes: A tecnologia usada permite uma melhor validação contudo não permite mandar mensagem de erro porque a tecnologia resolve o erro sozinha
Funciona com o primeiro Caracter.Complicado de se fazer pois a tecnologia está optimizada para o primeiro caracter.

## Slide 14: Document Managment
Mário Oliveira

## Slide 16: Project Quality
Carla Machado

## Slide 17: Processes and Process Analysis
Document Management Process
  It was followed in the majority of documents although some unconformities were detected
    Not following correctly the hierarchy for the different roles
  The process lacked flexibility in choosing the persons for the different roles
Project Assessment and Control Process
  Project and risk control weren’t very accurate
    Process wasn’t always exactly followed
    Problems with some of the used tools

## Slide 18: Processes and Process Analysis
Project Planning Process
  Plan was updated
    Redefinition of some concepts - milestones
Requirements Analysis Process
  Major unconformity
    changes were made that didn´t follow the change requirements process and documentation wasn’t updated

## Slide 19: Processes and Process Analysis
Review Process
  Major unconformity associated with the walkthrough
    The process wasn´t followed and measures weren’t recorded
Verification & Validation Process
  Doesn’t mention ad-hoc testing
    How to report defects not associated with tests
  What to do in cases of reopen
  Test plan wasn’t concluded

## Slide 20: Processes and Process Analysis
Common issues in following the processes
  Process measures weren’t always recorded or updated timely
  The processes weren’t always exactly followed as defined
  Some processes were overcomplicated for the team and project needs

## Slide 21: Quality Activities
Reviews
  Inspections
  Walkthrough
  Desk checks
Quality verifications
  Processes were followed
Testing
  Unit testing
  Acceptance and system testing

## Slide 22: Quality Cost
Task | Time
Reviews | 46
Quality verifications | 2
Test Planning | 48
Test Execution | 7.25
Chart: Quality Cost by Activity
| Reviews | Quality verifications | Test Planning | Test Execution
Time | 46 | 2 | 48 | 7.25

## Slide 23: Quality Perception

## Slide 24: Architecture
Rui Ganhoto

## Slide 26: Risk Management
João Girão

## Slide 27: Risk Management - Timeline
08/04/2013
KOM
Risks Identification:
Lack of knowledge on technology;
Project Plan is over budget
Mitigation Plan
(task plan for final week)
Risk meeting
Risk meeting
03/06/2013
Acceptance
Risk Minimization
(Lack of knowledge on technology)
Problem Identification
REESTIMATION
(Project Plan is over budget)
Risk Identifications
Risk Identifications
Risks Number: 2

## Slide 28: Risk Management
1º - Lack of knowledge on technology:
  Probability: 3
  Impact: 3
  Team Member: João Girão, Mário Oliveira, David Silva, João Martins, Carla Machado and Filipe Brandão
  Avoidance: To reduce probability all interfaces must be created and managed by Rui Ganhoto.
  Minimization: To reduce Impact Rui Ganhoto must give some formation to every team members.
  Contingency: Negotiate interface with the client and avoid WPF, windows forms would be an easier option for static content.

## Slide 29: Risk Management
2º - Project Plan is over budget
  Probability: 3
  Impact: 2
  Team Member: Everyone
  Resolved with the Reestimation
The project doesn’t end at the planned time (it’s a problem)
  Mitigation Plan: redistribution the tasks

## Slide 30: Product Demonstration
David João

## Slide 32: Analysis and Conclusions
Team

## Slide 33: Global

## Slide 34: Carla Machado

## Slide 35: David João

## Slide 36: Filipe Brandão

## Slide 37: João Girão

## Slide 38: João Martins
Main Contributions:
  Project plan process definition
  Verification and Validation process
  Test plan
Lessons Learned:
  Teamwork is important
  Communication is a must!

## Slide 39: João Martins
Lessons Learned:
  Test plan is not easy to make
  When anything can go wrong, it will go wrong.
  Participation in Team Results:
  Application Quality (Test plan)
  Do everything that it’s needed.

## Slide 40: Mário Oliveira

## Slide 41: Rui Ganhoto