## Slide 1: MIS – PS Keep Your Time

## Slide 2: Content

## Slide 3: Team Members
Carla Machado - Quality Manager
David João - Quality Engineer
Filipe Brandão - Project Manager
João Girão - Test Manager
João Guilherme Martins - Client Manager
Mário Oliveira - Librarian Manager
Rui Ganhoto - Technical Manager & Risk Manager

## Slide 4: Product Overview
João Martins

## Slide 5: Product Overview
  The Product Keep Your time will Allow users to manage their time in an easy and instinctively way by allowing to record the time spent on a task.
  In addition, this tool permits adding new tasks, selecting and viewing list of all incomplete tasks and their description.
  The users can start and stop time tracking anytime without having to think where to click.
  Later it’s possible to export all the data into a CSV sheet.

## Slide 6: Project Managment
Filipe Brandão

## Slide 7: Team Members
Carla Machado - Quality Manager
David João - Quality Engineer
Filipe Brandão - Project Manager
João Girão - Test Manager
João Guilherme Martins - Client Manager
Mário Oliveira - Librarian Manager
Rui Ganhoto - Technical Manager & Risk Manager

## Slide 8: Project Management
Filipe Brandão

## Slide 9: Life Cycle
Requirements Analysis
Design & Construction
Verification & Validation

## Slide 10: Milestones
Requirements Analysis
Design & Construction
Verification & Validation
KOM
8th April
SRS Review
6th May
Code Review
29th May
Acceptance
3rd June
Notes: KickOff Meeting - 8th of April
  The “Vision and Scope” and a project plan must be ready for presentation.
SRS Review – 6th of May
  Marks the end of the production of the SRS (meaning it is ready for review). REPLANNING
Code Review – 29th of May -> 1 June
  Marks the end of the coding phase. This means that the entire code and test plan must be ready.
Acceptance – 3rd of June
  Marks the end of the acceptance phase and the whole project. This means that all the software is testes and corrected.

## Slide 11: Deliverables
Vision and Scope
Software Development Plan
Quality Plan
Test Plan
Software Requirements Specification
Risk Plan
Software source code and binaries
Review Reports
Weekly Reports
Post-Mortem Report

## Slide 12: Effort Estimation
Planning Poker was the technique used for effort estimation
  Time during discussions was controlled
Work Breakdown Structure was built and discussed right before the estimation.
Two estimations were performed :
  Before KOM
  After “SRS Review” milestone
Notes: Planning poker -> fast estimation -> fast discussion

## Slide 13: Effort Estimation
Chart: Effort Estimation
| Requirements Analysis | Design & Construction | Verification & Validation | Weekly tasks
Estimation 1 | 100 | 95 | 26
Estimation 2 | 93 | 16 | 13.5
Notes: FONTE DOS VALORES : BREAKDOWN (EV)
Coding da estimation 2 já não inclui CI – MEETING
First estimation -> conding não tem android

## Slide 14: Effort Estimation
Chart: Estimation vs Reality
| Requirements Analysis | Design & Construction | Verification & Validation | Weekly tasks
Estimation | 100 | 109 | 16 | 13.5
Reality | 107.75 | 73.75 | 8 | 9.75
Notes: -39,25h horas de diferença entre o real e a estimação
FONTE DOS VALORES : BREAKDOWN (EV)

## Slide 15: Real Effort
But according to the individual logs…
Chart: Effort by Phase
| Processes Definition | Requirement Analysis | Design & Construction | Verification & Validation | After Due date
 | 262 | 119.75 | 124.75 | 9 | 8
Notes: Process Definition : Week 1 to Week 7 - expected 252h
Requirements: Week 8 to Week 10 -
Coding: Week 10 to 15 minus Testing
Testing : sum of testing tasks
Project expected:

## Slide 16: Effort by Task Type
Task Type | Hours | Percent
Documentation | 230,75 | 41%
Meetings/Discussions | 75 | 14%
Coding | 65,25 | 12%
Research/Study | 58 | 10%
Revision | 46 | 8%
Requirements | 33,5 | 6%
Project/Quality/Risk Management | 22,5 | 4%
Repository Management | 14 | 3%
Testing | 7,25 | 1%
Bug fixing | 6,25 | 1%
Notes: INCLUDES PROCESSES DEFINITION

## Slide 17: Individual Effort
Chart: 
| CM | DJ | FB | JG | JM | MO | RG | EXPECTED
Processes | 40.5 | 35 | 43.25 | 34.5 | 37 | 36.5 | 35.25 | 36
Project | 45.5 | 37.25 | 36.75 | 40 | 39.5 | 46.75 | 43.5 | 42
After Due Date | 3 | 1 | 3.75
Notes: Processes = 6 weeks
Project = 7 weeks

## Slide 18: Weekly Individual Effort
Chart: 
| CM | DJ | FB | JG | JM | MO | RG
Min | 5.5 | 2.5 | 4 | 7 | 3 | 5 | 2
Max | 8.5 | 7.5 | 13.25 | 3.5 | 7.5 | 8 | 9.25
Mid | 6.6154 | 5.5577 | 6.1538 | 5.7308 | 5.8462 | 6.4038 | 6.0577
Notes: overwork

## Slide 19: Management & Control
Software Development Plan
  Centralized information
Microsoft Project for scheduling and allocation
  Easier scheduling
  What’s the next task at any given time
Earned Value Graph in Microsoft Excel for project control based on WBS tasks
  Haven’t used its full potential.
Notes: SDP -> plano inicial para KOM -> rework depois da KOM -> redefinição Milestones
Various problems on EV:
bad wbs -> TAREFAS NOVAS ---- QUAIS???
1 task -> 1 member
bugs when changed
Levou-nos a fazer um plano especial para a ultima semana

## Slide 20: Management & Control
Earned Value Graph

## Slide 21: Management & Control
Weekly reports
  Weekly analysis
Individual logs
  What was done, when it was done, how much did it cost.

## Slide 22: Product
João Martins

## Slide 23: Requirements
Number of Initial Requirements
66
Number of Delivered Requirements
64

## Slide 24: Requirements
Requirements | Nº | Requirements Delivered | Requirements not Delivered
Functional | 53 | 51 | 2
Interface | 11 | 11 | 0
Performance | 2 | 2 | 0
Total | 66 | 64 | 2

## Slide 25: Requirements conclusion
97% of the Requirements were delivered
Requirements not Delivered:
12CIT-003:ConfigureInactiveTime.Validate.False
1CT-004:Task.create.AutoComplete
Notes: A tecnologia usada permite uma melhor validação contudo não permite mandar mensagem de erro porque a tecnologia resolve o erro sozinha
Funciona com o primeiro Caracter.Complicado de se fazer pois a tecnologia está optimizada para o primeiro caracter.

## Slide 26: Document Managment
Mário Oliveira

## Slide 27: Document repository

## Slide 28: Document Repository
Google Code
  Keep Your Time Project
  Documentation
    Meetings
    Processes
    Project Management
    Templates
    Test Results
    Weekly Reports

## Slide 29: Document Repository
Google Docs
  Documents, Requirements, Tests and Review Measures
  Dashboard
  Logs

## Slide 30: Document Repository
Google Sites
  Project Information
  Dashboard
  Repository
      Logs (link)
      Project Documentation
      Templates
      Processes
      Weekly Report
      Meeting minutes
      Kickoff Meeting
      Code Repository (link)

## Slide 31: Document Repository
Documents state
  Draft: 2
  Ready for Revision: 0
  Ready for Approval: 0
  Baselined: 29
  Deprecated: 0
  Global Change Rate: 0,066

## Slide 32: Project Quality
Carla Machado

## Slide 33: Processes and Process Analysis
Document Management Process
  It was followed in the majority of documents although some unconformities were detected
    Not following correctly the hierarchy for the different roles
  The process lacked flexibility in choosing the persons for the different roles
Project Assessment and Control Process
  Project and risk control weren’t very accurate
    Process wasn’t always exactly followed
    Problems with some of the used tools

## Slide 34: Processes and Process Analysis
Project Planning Process
  Plan was updated
    Redefinition of some concepts - milestones
Requirements Analysis Process
  Major unconformity
    changes were made that didn´t follow the change requirements process and documentation wasn’t updated

## Slide 35: Processes and Process Analysis
Review Process
  Major unconformity associated with the walkthrough
    The process wasn´t followed and measures weren’t recorded
Verification & Validation Process
  Doesn’t mention ad-hoc testing
    How to report defects not associated with tests
  What to do in cases of reopen
  Test plan wasn’t concluded

## Slide 36: Processes and Process Analysis
Common issues in following the processes
  Process measures weren’t always recorded or updated timely
  The processes weren’t always exactly followed as defined
  Some processes were overcomplicated for the team and project needs

## Slide 37: Quality Activities
Reviews
  Inspections
  Walkthrough
  Desk checks
Quality verifications
  Processes were followed
Testing
  Unit testing
  Acceptance and system testing

## Slide 38: Quality Cost
Task | Time
Reviews | 46
Quality verifications | 2
Test Planning | 48
Test Execution | 7.25
Chart: Quality Cost by Activity
| Reviews | Quality verifications | Test Planning | Test Execution
Time | 46 | 2 | 48 | 7.25

## Slide 39: Quality Perception
Processes weren’t always exactly followed
  Some situations were overlooked
Test Plan
Times spent testing
Application is functional
  Level of confidence – 70% a 80%

## Slide 40: Architecture
Rui Ganhoto

## Slide 41: Architecture
Tools
Layer Model
  Development Architecture
  Database
Main Features

## Slide 42: Tools
Microsoft Visual Studio
SubMain GhostDoc
Enterprise Architect

## Slide 43: Layer Model
From Visual Studio
  WCF
  C#
  SQL CE

## Slide 44: Development Architecture
Multiple User Controls
  Each with is own functionality
  Communication between user controls with Events
Available Events
  OnTaskListChanged
  OnTaskUpdated
  OnTimeAdded
  OnTaskDeleted
  OnStartTaskPressed
  OnStopTaskPressed
  OnTaskCreated

## Slide 45: Database

## Slide 46: Main Features
Task Tracking
Accessing user activity

## Slide 47: Risk Management
João Girão

## Slide 48: Risk Management - Timeline
08/04/2013
KOM
Risks Identification:
Lack of knowledge on technology;
Project Plan is over budget
Mitigation Plan
(task plan for final week)
Risk meeting
Risk meeting
03/06/2013
Acceptance
Risk Minimization
(Lack of knowledge on technology)
Problem Identification
REESTIMATION
(Project Plan is over budget)
Risk Identifications
Risk Identifications
Risks Number: 2

## Slide 49: Risk Management
1º - Lack of knowledge on technology:
  Probability: 3
  Impact: 3
  Team Member: João Girão, Mário Oliveira, David Silva, João Martins, Carla Machado and Filipe Brandão
  Avoidance: To reduce probability all interfaces must be created and managed by Rui Ganhoto.
  Minimization: To reduce Impact Rui Ganhoto must give some formation to every team members.
  Contingency: Negotiate interface with the client and avoid WPF, windows forms would be an easier option for static content.

## Slide 50: Risk Management
2º - Project Plan is over budget
  Probability: 3
  Impact: 2
  Team Member: Everyone
  Resolved with the Reestimation
The project doesn’t end at the planned time (it’s a problem)
  Mitigation Plan: Task redistribution
    Analysis of incomplete tasks and remaining time for each one.

## Slide 51: Product Demonstration
David João

## Slide 53: Analysis and Conclusions
Team

## Slide 54: Global

## Slide 55: Carla Machado
Main contributions
  English revisions
  Enterprise Architect knowledge
  Testing
Participation analysis
  Positive
  Work done, availability to help and overwork when required

## Slide 56: Carla Machado
Lessons Learned
  Organization
  Level of commitment and motivation
    similar for all members
    Maintain it throughout the project
  Working together and regular meetings
  Take advantage of individual strengths and knowledge

## Slide 57: David João

## Slide 58: Filipe Brandão

## Slide 59: Filipe Brandão - Contributions
  Previous experience :
    allowed a more direct approach to the problems presented
    allowed me to help other members providing guidance

## Slide 60: Filipe Brandão - Lessons Learned
Project Management is a lot about experience, learning lessons and adapting based on all the previous information.
Soft skills are necessary: communication, leadership, handling different personalities, etc.
A tool, doesn’t matter how many value it can add to our work, is worth nothing if not correctly used.
Regular meetings are essential. Working together is beneficial.
Project control implies different aspects depending on the project state.
Transparency during the whole project is essential.
Motivation is key.

## Slide 61: Filipe Brandão - Lessons Learned
A good Work Breakdown Chart is a good foundation for the project plan.
Earned Value Graph tasks should be related to one member. If more members are allocated to that task, repeat it.
Project Planning Process seemed OK for this project but should be added hints on how to develop a good WBS.
Regarding tools, SVN is to keeper. Facebook is good for communication but it doesn’t have search functionality.

## Slide 62: João Girão
Main Contributions:
  Writing and discussing some processes;
  Vision and Scope;
  SRS and Requirements Definition;
  Coding some features;
  Testing;
Chart: 
| Meetings/Discussions | Documentation | Revision | Requirements | Coding | Testing | Bug fixing | Repository Management | Research/Study | Project/Quality/Risk Management
Effort | 10 | 32.75 | 0.25 | 10 | 11 | 1.5 | 0 | 1.5 | 7 | 0

## Slide 63: João Girão
Participation analysis: Positive
  Self-help;
  Interested;
  Organized;
  Critical attitude;
Lessons Learned:
  For project successful:
    Team motivation;
    Team organization;
    Responsibility of each member;
  Project Plan is very important;
  Regular meetings are very important;

## Slide 64: João Martins
Main Contributions:
  Project plan process definition
  Verification and Validation process
  Test plan
  Settings code
Lessons Learned:
  Teamwork is important
  Communication is a must!

## Slide 65: João Martins
Lessons Learned:
  Test plan is not easy to make
  When anything can go wrong, it will go wrong.
  Participation in Team Results:
  Application Quality (Test plan)
  Do everything that it’s needed.

## Slide 66: Mário Oliveira
Main contributions
  Updating the repository
  Writing some processes
  SRS and Requirements Definition
  Review and approval of some documents
  Coding some features
Participation analysis
  Helped when required
  Did the assigned tasks
  Interest in the project

## Slide 67: Mário Oliveira
Lessons Learned
  Teamwork is the key to sucess
  The structure of the application should be well planned

## Slide 68: Rui Ganhoto
Main Contributions
  Software Main Idea
  Technical Knowledge and Helping the whole team in developing their assignments
  Software Base Architecture, Functionality and UI Development
  Help In Requirement definitions when prompted
  Trying to help the team thinking about the future helping them get focused

## Slide 69: Rui Ganhoto
Participation in Team Results
  Active participation
  Always trying to help my coworkers when necessary
  Good commitment and positive participation in the team
  While developing, I tried to keep the team focused on the task
Lessons Learned
  It's not easy to keep a big team to work in synchrony
  Rigid documents that doesn't predict exceptions, sometimes will not fit in reality.