## Slide 1: Keep Your Time
Kickoff meeting

## Slide 2: Index
Team Introduction
Vision and Scope
Development Plan
Quality Plan

## Slide 3: Team Introduction
Team name : Ps2win

## Slide 4: Team Members
Carla Machado - Quality Manager
David João - Quality Engineer
Filipe Brandão - Project Manager
Rui Ganhoto - Technical Manager & Risk Manager
João Girão - Test Manager
João Guilherme Martins - Client Manager
Mário Oliveira - Librarian Manager

## Slide 5: Vision And Scope

## Slide 6: Keep Your Time
The time spent in individual tasks is an increasing concern for everyone;
Business:
  Costs and deadlines are a major concern;
  The time management doesn’t always receive the required attention or isn’t controlled in an appropriate manner.
Time Tracking and Task Management System

## Slide 7: Objectives
Increase people’s efficiency and performance;
Assist a person to focus on a certain task;

## Slide 8: Business Risk
Poor adherence by people

## Slide 9: Software
Functional
Portability
Interactivity
Task Time Management:
Adding, editing and deleting tasks;
Group tasks; (Release 2)
Inactivity alerts;
Registering and timing individual tasks;
Exporting data; (Release 2)
Communication
Start/Stop time tracking; (Release 2)
Adding new tasks; (Release 2)
Selecting and viewing tasks; (Release 2)

## Slide 10: Software
Assumptions:
  The computer will have:
    Windows OS (at least the Vista version);
    Framework .NET 4.5;
  The Smartphone will have:
    An Android platform;
    Wireless technology.
  The computer and the smartphone must be connected to the same network

## Slide 11: Development Plan

## Slide 12: Life Cycle
Requirements Analysis
Design & Construction
Verification & Validation

## Slide 13: Schedule
Total Effort : 255,45 hours
Slack : 40,55 hours

## Slide 14: Life Cycle
Chart: 
| Requirements Analysis | Design & Construction | Verification & Validation
Effort hours (aprox) | 115 | 106 | 34

## Slide 15: Resources
Chart: 
| Carla Machado | David João | Filipe Brandão | João Girão | João Martins | Mário Oliveira | Rui Ganhoto
Effort hours (aprox) | 29 | 44 | 29 | 39 | 37 | 39 | 36

## Slide 16: Deliverables
Vision and Scope
Software Development Plan
Quality Plan
Test Plan
Software Requirements Specification
Risk Plan
Software source code and binaries
Review Reports
Post-Mortem Report

## Slide 17: Tracking and Control
  Earned Value Graph
  Risk Planning as part of a well tailored Assessment & Control Process
  Weekly work logs
  Weekly Reports

## Slide 18: Quality Plan

## Slide 19: Quality Plan
Quality goals
  Assure all processes are followed
  Assure the realization of reviews both to documents and code
    Inspections
    Walkthrough
    Deskcheck
  Coding Standards are defined and followed

## Slide 20: Quality Plan
Quality goals
  Assure the testability of the application
    Unit testing
    Acceptance testing
  Assure the usability of the application
Quality Records
  A record of the unconformities found will be kept
  Corrective actions will be decided and performed

## Slide 21: Questions?